# FAMILY LEADERSHIP TEAM IMPLEMENTATION CHECKLIST

For use with your school’s Family Leadership Team (FLT) throughout the school year.

# Prepare and Plan: Before School Starts (June–August)

- Identify 8–12 potential parent leaders

- Conduct personal outreach (calls/texts from admin or current FLT parents)

- Prepare a “What Is FLT?” packet or flyer

- Set meeting dates for the fall semester

- Identify needed resources: childcare, interpreters, meals

- Set up communication channels (Remind, Facebook group, WhatsApp, email)

# Launch the School Year FLT Team: Early Fall (August–September)

- Hold an FLT welcome meeting

- Review goals and expectations

- Identify family strengths, interests, and preferred roles

- Share school events calendar for co-planning

- Introduce the K20 QUEST app and resources

- Check dates for GEAR UP for LIFE Fall 2026 Family Leadership Academy Workshops

# Build Momentum: Fall (October–December)

- Ensure FLT members have meaningful roles

- Use family listening sessions or surveys to gather broader input

- Co-plan at least one event for families (could be Spring Family Night in connection with FLA)

- Spotlight FLT parents (school website, social posts, shout-outs)

- Check in with members about support needs

# Leadership Development and Partnership: Early Spring (January–March)

- Involve FLT in 10th/11th grade transition and postsecondary work

- Recruit additional families through FLT members (e.g. with a “bring-a-friend” initiative)

- Continue building relationships with administrators and teachers

- Host GEAR UP for LIFE Spring Family Night focused on Oklahoma’s Promise

# Celebrate and Sustain: Late Spring (April–May)

- Celebrate accomplishments (certificates, recognition, photos)

- Gather feedback on the year

- Identify returning members

- Identify new families to recruit for next year

- Create a preliminary FLT calendar for the new school year